## Ago 05
FOLLOW-UP MECHANISM FOR THE IMPLEMENTATION OF THE
INTER-AMERICAN CONVENTION ON THE PREVENTION, PUNISHMENT, AND ERADICATION OF VIOLENCE AGAINST WOMEN
CONVENCION BELEM DO PARA (MESECVI)
COMMITTEE OF EXPERTS (CEVI)
ANNUAL WORK PLAN
AUGUST 2005 – AUGUST 2006
**
DATE | ACTIVITY | Aug. 05 |  |  |  | Sep. 05 |  |  |  | Oct. 05 |  |  |  | Nov. 05 |  |  |  | Dec. 05 |  |  |  | Jan. 06 |  |  |  | Feb. 06 |  |  |  | Mar. 06 |  |  |  | Apr. 06 |  |  |  | May 06 |  |  |  | Jun. 06 |  |  |  | Jul. 06 |  |  |  | Aug. 06
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
August 22 - 24 | CEVI Meeting
Approval of the rules of procedure, questionnaire, annual work calendar and distribution of work
November 7 | The questionnaire is sent to competent national authorities
February 15 | Deadline for submitting the replies to the questionnaire
February 28 | The country reports are sent to the Experts
April 17 | Deadline to send the drafts of the preliminary report to the Secretariat of the CEVI
May 1 | The drafts of the preliminary report are sent to the other members of the subgroup
July 24 - 25 | CEVI Meeting
First multilateral evaluation meeting
August 30 | Deadline for experts to send questions/information
Committee of Experts
Secretariat of the CEVI
The States provide information
Conference of States Parties
Experts

## Ago 06
FOLLOW-UP MECHANISM FOR THE IMPLEMENTATION OF THE
INTER-AMERICAN CONVENTION ON THE PREVENTION, PUNISHMENT, AND ERADICATION OF VIOLENCE AGAINST WOMEN
CONVENCION BELEM DO PARA (MESECVI)
COMMITTEE OF EXPERTS (CEVI)
ANNUAL WORK PLAN
AUGUST 2006 – AUGUST 2007
**
DATE | ACTIVITY | Sep. 06 |  |  |  | Oct. 06 |  |  |  | Nov. 06 |  |  |  | Dec. 06 |  |  |  | Jan. 07 |  |  |  | Feb. 07 |  |  |  | Mar. 07 |  |  |  | Apr. 07 |  |  |  | May 07 |  |  |  | Jun. 07 |  |  |  | Jul. 07 |  |  |  | Aug. 07 |  |  |  | Sep. 07
|  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
October 20 | Deadline for answers reception/information of ANC
**
October 30 | Answers and reports are send to the competent national autorithy
December 15 | Deadline for experts to submit preliminary reports to the CEVI's Secretariat
December 29 | Preliminaries reports are send to the competent national authority
February 23 | Deadline for submitting comments or clarifications by the States
March 15 | The comments or clarifications are sent to the Experts
May 10 - 11 | CEVI Meeting
Second multilateral evaluation meeting
August 16 - 17 | CEVI Meeting
Third multilateral evaluation meeting: approval of the final report
September 20 - 21 | Conference of States Parties
**
September 28 | Annual activity report
Committee of Experts
Secretariat of the CEVI
The States provide information
Conference of States Parties
Experts